Faculty of Computer and information

Under supervision of

Ibrahim El-Semman

Project Name

Easy Parking



- Mostafa Mohamed Ahmed Fouad

- Mahmoud Ayman Hashem Abd-ElRahman

- Mahmoud Ali Abd-Elftah Abd-Elhafez

- Yasmeen Khaled Farhan Ahmed

- Mariam Alaa El-Din Abd-ElWahed

Project Charter

- Official project name: Easy Parking

- Project sponsor: Traffic department

- Project manager:  Mostafa Mohamed Ahmed

- Project members:

Mostafa Mohamed - Mahmoud Ayman -    Mahmoud Ali   - Yasmeen Khaled -

Mariam Alaa

- Project Purpose :

Helping people to parking their cars easily via using an application that can find an empty parking for them.

- Assumption:

- will get all resources required.

- make a regular meeting with the team.

- collect data from stakeholders and review the team progress with them

- Summary :

Parking is a major problem in both developed and developing countries. The main cause of the problem is a severe discrepancy between the locations of parking and number of vehicles with the advancement of technology, there are attempts to find smart solutions for this crisis .one of them is smart parking applications
The cameras in shops are used and a connection is made with the application, so that the user logs into the application and specifies the name of the street in which the stop is required and is connected to the cameras on the street so that the cameras show the driver's free spaces.

Project Scope

- Objectives:

Reduce traffic jams.

Keep income for necessities of life.

Reduce accidents and crashes which happen when people park.

See the parking space size.

- Deliverables:

Permission from shop owners to use their cameras.

Software.

Data base.

Integration.

- Millstones:

- Requirements review : Requirements specifications are complete, correct, approved and suitable. By 1/11/2021

- Critical design review: Detailed designs fully implement the system architecture, are approved and are suitable for input into the development of code. By 15/11/2021.

- System test review : The software product has passed system testing and is suitable for input into acceptance testing.by 3/2/2022

- Product operational: The software is in use in its target operational environment.by 17/2/2022.

- Project Resource:

Hardware : 10 PC , 3 Servers.
Staff: team android developers , UI designer , team network Engineer .

- Budget:

budget allocated for this project is 600000 L.E (including servers, devices, developers and training).

- Communication management:

1- Conducting a weekly meeting between each department and the
leader to discuss and solve problems and discuss suggestions to
improve the quality of the application.
2- Meeting between the heads of the departments and the head of
the company to discuss the latest developments

- Limits & Exclusions

- Limits :

The project must be ready at the end of February.

The application must connect to the cameras to know the nearest and best place for the user.

The application will be for Android  .

- Exclusions :

The project don’t use sensors.

The project don’t have responsibility for security of the shops.

There is no wages for the owners of the shops.

The application will not be for web .

WBS Structure

WBS Dictionary

| Work Package | ID | Responsible | Start Date | End Date |
| --- | --- | --- | --- | --- |
| Permission from shop | A | Mahmoud Ali | 24/11/2021 | 29/12/2021 |
| UI design | D | Mariam | 29/12/2021 | 12/1/2022 |
| Android App design | E | Mostafa | 29/12/2021 | 19/1/2022 |
| Network processing | F | Yasmeen | 29/12/2021 | 5/1/2022 |
| gathering information from Zone Traffic Department | G | Mahmoud Ali | 29/12/2021 | 5/1/2022 |
| Reserve a server in Google cloud | H | Yasmeen | 29/12/2021 | 5/1/2022 |
| Test | I | Mahmoud Ayman | 19/1/2022 | 3/2/2022 |
| Integration | J | Mahmoud Ayman | 3/2/2022 | 17/2/2022 |

Project Network

Id           description 		                                        Preceding activity                 duration

A            Permission from shop owners     		     none                                     5

B            UI design                                                                A                	2

C            Android app design                                               A		                              3

D             Network processing                          		       A			                    2

E            Reserve a server in Google cloud      		       A		                               1

F             Gathering information	               		       A		                               1

G            Test                                                 		       B, C, D	                               2

H              Integration                                                            E, F                                     2

Responsibility matrix

| Name of responsible task | Mariam | Mahmoud Ayman | Mahmoud Ali | Mostafa | yasmen |
| --- | --- | --- | --- | --- | --- |
| Permission from shops |  | R |  |  | A |
| UI design | R |  |  |  |  |
| Android app design |  |  |  | R |  |
| Network processing |  |  |  |  | R |
| Test | A |  | R | A |  |
| Reserve a server in Google cloud |  |  |  |  | R |
| gathering information from Zone Traffic Department |  | R |  |  |  |
| full test |  |  | R | A |  |

Resource Constrained

| ID ID | RES | DUR | ES | LF | SL | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | 2 | 5 | 0 | 5 | 0 | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |  |  |
| B | 1 | 2 | 5 | 8 | 1 |  |  |  |  |  | 1 | 1 |  |  |  |  |  |
| C | 1 | 3 | 5 | 8 | 0 |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  |
| D | 1 | 2 | 5 | 8 | 1 |  |  |  |  |  | 1 | 1 |  |  |  |  |  |
| E | 1 | 1 | 5 | 10 | 4 |  |  |  |  |  | 1 |  |  |  |  |  |  |
| F | 1 | 1 | 5 | 10 | 4 |  |  |  |  |  | 1 |  |  |  |  |  |  |
| G | 3 | 2 | 8 | 10 | 0 |  |  |  |  |  |  |  |  | 3 | 3 |  |  |
| H | 2 | 2 | 10 | 12 | 0 |  |  |  |  |  |  |  |  |  |  | 2 | 2 |
| Total Resource Load |  |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 5 | 3 | 1 | 3 | 3 | 2 | 2 |
| Resource Available |  |  |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |

Budget Baseline

| ID | DUR | Task | Budget | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | 5 | Permission from shop | 100 | 20 | 20 | 20 | 20 | 20 |  |  |  |  |  |  |  |
| B | 2 | UI design | 14 |  |  |  |  |  | 7 | 7 |  |  |  |  |  |
| C | 3 | Android App design | 30 |  |  |  |  |  | 10 | 10 | 10 |  |  |  |  |
| D | 2 | Network processing | 30 |  |  |  |  |  | 15 | 15 |  |  |  |  |  |
| E | 1 | Reserve a server in Google cloud | 5 |  |  |  |  |  | 5 |  |  |  |  |  |  |
| F | 1 | gathering information from Zone Traffic Department | 25 |  |  |  |  |  | 25 |  |  |  |  |  |  |
| G | 2 | Test | 20 |  |  |  |  |  |  |  |  | 10 | 10 |  |  |
| H | 2 | Integration | 10 |  |  |  |  |  |  |  |  |  |  | 5 | 5 |
| Total |  |  | 52 | 20 | 20 | 20 | 20 | 20 | 62 | 32 | 10 | 10 | 10 | 5 | 5 |
| Commutative |  |  |  | 20 | 40 | 60 | 80 | 100 | 162 | 194 | 204 | 214 | 224 | 229 | 234 |

Risk Management

| Risk description | Probability risk | Impact of risk | Risk category | Action of risk |
| --- | --- | --- | --- | --- |
| The location that the user will impact may be not clear | Medium | High | Performance | Input a detailed location |
| Poor resource plans result to delaying deadlines of the final product | Medium | High | Resource | Resources should be allocated before a project begins |
| The project cost risk is the risk that a project will spend more money than was originally budget | High | High | Budget | Ensuring strong plans are done for budget time and for tasks |